INTERNAL EVALUATION POOLS-T 141783-LLP-1-2008-1-DK-LEONARDO-LMP

Partner: All partners
 
Date:   April 21st  2010
Period Covered by this Review: January 1st 2010 to March 31st 2010
Please complete this form to record the activities and progress in the period.

	Communication:

Which partners have you had communications with?

How often and in which way have you communicated with partners?
	There have been contacts between all partners at least three to four times per month

Most communication has been through e-mail. Communication by phone has also been used frequently for debates with NL and UK teams. 

Communication by phone has also been used between EL and NL teams.

Project meeting in March with all teams



	Innovatory aspects:

Describe any innovatory aspects to your activities.
	Use of Facebook to disseminate the project.

Multidict development.  Multidict now remembers via a cookie the user’s previous choice of target language and dictionary, enabling it to be integrated fully for the first time with the Textblender.  JavaScript has improved its interactivity and clarity for the user, and so also has the introduction of favicons to represent the dictionaries.

We have embedded the use of WORDLINK in a Dutch manual for international work placements. (see attachment). This is distributed to 35,000 students in NL.


	Management:

Do you feel that information relating to the management of the project is sufficient, relevant and effective? (Please comment).

Give a rating on a scale of 5 to  1.  

5 being the most positive.
	The administration system is efficient with all project costs separated with unique activity numbers according to type etc.

The project continues to be effectively managed. Information is plenty and pragmatic.

The management of the project, is sufficient, relevant and effective.

5 (All partners scored 5)



	Dissemination:

List of dissemination activities you have been engaged in.
	Newsletter prepared and mailed to our registered 761 users.

The project will be disseminated  with a paper presentation at EuroCall 2010. We have just received the acceptance letter

Continued correspondence with HMIe, the Scottish education inspectorate about Sector Leading Innovative Practice aspects of POOLS projects. Features in the Island Voices blog.

Multidict links added to all Gaelic terminology database search results on SMO website.
Presentation to sector management

Presentation at AOC Clusius teams in Hoorn (follow-up from previous activity)
Newsletters and information on project’s progress were mailed to all vocational training centres, certified language trainers in vocational training and all the other organizations that already were familiar with the project (from previous contact).


	External impact/mainstreams:

Any multiplier effect/impact.
	Two other projects have agreed to make use of the Wordlink and TextBlender, this means that the software is now also being used in Portugal, Turkey, and Lithuania

The touristic school in Alexandroupolis is expected to use and test the examples made by us using the WPTB (for waiters) in their courses


	Overall comment:


	The project is on track. The new version with improved layout of the TextBlender seems promising.

Project is going as planned! We are now in the process of translating the manual.



	Summary of Local Activities in the period:

Main activity in the period has been programming and testing the TextBlender tool. The tool has been rewritten based on the testing of and feedback received from the previous versions. The new version is based on a step by step approach and the actual “engine” has been improved. The new version has support for graphics in different sizes, “automatic” inclusion and copying of media files through a browse file system. 

We have actively disseminated the project results, e.g. edited / compiled the project newsletters and updated the website. 

Continued dissemination and software development. See also http://www.smo.uhi.ac.uk/~caoimhin/obair/pools-t/twitter.html
Introduction of TextBlender and Wordlink to Horizon College departments, and Clusius College departments.

Main activity in the period has been testing the TextBlender and wordlink and exchanging comments within the Greek group and with the other partners.
Preparation of teaching material using the WPTB (www.athenavtc.gr/waiter ). 
Pilot testing of teaching materials prepared for a course for waiters.

Introduction of the project tools and the teaching materials prepared from our college to the Touristic school of Alex/polis. 
Meeting in Holland with the Dutch and Greek partners for CLIL manual. 
Meeting in Brussels with all partners.
Newsletters and information on project’s progress were mailed to all vocational training centres, certified language trainers in vocational training and all the other organizations that already were familiar with the project (from previous contact).


	Milestones met:

Project newsletter produced as planned. 

Quarterly reports compiled and made online

DVDs with final version of the TextBlender tool and a DIY DVD were handed out during a project meetings in two related language projects (pools-m and pools-2)

manual is being translated.

Testing of new TextBlender versions takes place with classes at Horizon College.

Dissemination has been continued.

Testing of the tools from team members and trainers.
Preparation of examples using WPTB and pilot testing has been completed.


	Delays (if any) in planned activities and outputs:

None


	If applicable how will the team compensate for the delays and catch up:

N.a.


	Other comments:

The project is on track.



Partnership progress review Page 1 of 1

