POOLS-m project meeting in Istanbul 3. to 4. May 2011

Main issues for the meeting:

- Quality control

- Evaluation of the first teacher training courses

- Evaluation for the edited manuals

- Dissemination

- Status of the surveys

NB. The schedules are only indicative as the agenda should be flexible and other items may be included. Where needed/possible we may also break into groups

3. May 2011

9.00 Departure from hotel

Agenda:

- Status and quality control

- Work tasks and project plan - follow up on decisions from last meeting

- Newsletter

- Dissemination – short input from each partner

- Interim report – feed back

- The website (Kent). A quick run through and status

- Evaluation of teacher training courses so far: Presentation from each partner (max. 30 minutes for each presentation.)

- Status of the use of the surveys. (SUPSI)

- Language Learning Methods, film ( SUPSI)

4. May 2011

9.00: Departure from hotel

- Lay-out of manuals and mobility guide: Evaluation of the final edited version.

- External evaluation ( Gareth and Angelica)

- Things to improve and good ideas for the last phase of the project.

- Tasks and milestones per partner until next meeting. Each partner to bring or to submit a schedule / list of milestones before the meeting

- Conclusions, next milestones and evaluation

- End of meeting

Milestones from last meeting

## Turkish team

- Teacher training courses to be set dating from January,2011 to May 2011( 5 teacher training courses to be held )

- The last teacher training program ( 6th teacher training course program ) to be held in Bodrum Marmara Private Educational Institutions in July, 2011

- Proofreading and Translating the guides are to be accomplished by 31 December

- Giving feedback about the course design that is to be prepared by Danish Team in November

- Translating the course design into Turkish language by mid December

- 3rd quarterly report to be submitted to Danish Team by 12 November

- Articles essays considering TBL and PHYEMOC are to be published either in the late months of 2010 or very early months of 2011

## Partner: Marijampole VET Centre	 	Date: November 5, 2010

Period : from Pistioa to Istanbul and the end of 2010

| ACTIVITIES | DEADLINES | RESPONSIBLE |
| --- | --- | --- |
| Minutes of Pistoia meeting discussed and given feedback, a short article on www.mprc.lt | November 10, 2010 | Jolita |
| Finish translating of all manuals, send manuals one by one, once it has been edited | December 31, 2010 | Rasa and Jolita |
| 3rd Quarterly report | November 12, 2010 | Rasa |
| 4th Quarterly report – | December 15, 2010 | Rasa |
| Contacts with schools and future course participants | November- December 2010 | Rasa and Jolita |
| Contacts with Marijampole Teachers’ Training College | November 2010 | Jolita |
| Course guide to be sent by Stefan and translated | By the end of December 2010 | Rasa & Jolita |
| Start of teachers’ training courses | February 2011- April 2011 | Rasa & Jolita |
| Dissemination article in Dialogue (monthly newspaper for teachers, edited by Ministry of Education and Science of LT) | Until April 2011 | Rasa and Jolita |
| Training course for students of Marijampole teachers’ training college | February/March/ 2011 | Jolita& Rasa |
| Observing lessons of the future teachers/methods being implemented; video recording of the cases | March 2011 | Jolita & Rasa |
| Dissemination – a reportage with regional TV, interview with Cecilia- (please, be well prepared and good looking, Cecilia() | All period, in April when Cecilia is here | Jolita & Rasa |

## SUPSI MILESTONES FOR MAY 2011

- Exploring the possibility of creating an on-line student and teacher  satisfaction survey.  If feasible, this survey will be set up and made available via link on languages.dk webpage

- Test this survey with our students and teachers

- Translating the IWP Guide into German

- Consider the possibility of translating the new versions of the 5 manuals into German

- Creating 2 lesson plans based on 2 of the methods and filming the main of the phases of the lessons in class

- Filming a group of students playing an adapted version of the Work Placement Game.

- Actively encourage our team of SUPSI language teachers to use the methods in their classes

## CSCS Milestones

- November 2-3, 2010: training (Danish team) – Group A of participants

- November 5, 2010: sending the IWP table to Kent (the orange table for the IWP game)

- November 8, 2010: translation of the brochure into Italian

- December 15, 2010: article for the newsletter to be sent to Kent

- December 17, 2010: Integration of the Teacher training course  for GROUP A (How to write a simulation?) + follow up + coaching (presenting the online Pools- M platform in Italian)

- December 22 and 23, 2010: Christmas greetings to the participants GROUP A with the newsletter and some ready to use materials in Italian, plus questions to be answered during the winter break: did you use the methods? Which was the target? How did it go? How many students participated? How can we help?

- December 22 and 23, 2010: Christmas greeting to the list of institutions, schools, language schools, high-schools, sending them the newsletter of the Pools M project

- December 31, 2010: setting up the Italian online platform for feed-back, forum, pool of knowledge, sharing, etc. and preparing the invitation to the follow up

- December 31, 2010: quarterly report and interim report to be sent to Kent and Lone

- January 3-10, 2011: article for the Italian National Agency to be published on their website + brochure with the training to be organized in February 2011

- January 1-31, 2011: dissemination and promotional activities across Italy for the February and April editions of the TOT

- February 17-18, 2011: training in Pistoia: GROUP B

- February 25, 2011: contacts with the participants of the first training (GROUP A) for a survey on how they implement the methods… results? Problems? Issues they might want to talk about?

- March 7, 2011: contacts with the participants of both GROUPS A and B with the brochure of the Follow Up organized on March 18, 2011

- March 18, 2011: integration (debate) + follow up + coaching GROUPS A and B

- March 25, 2011: article to be sent to Kent for the newsletter + quarterly report

- April 1st, 2011: e-mail to ALL CONTACTS with the brochure for the third training (GROUP C).

- April 14 and 15, 2011: training GROUP C -

- May 2- 5, 2011: project meeting in Istanbul

- May  10, 2011: contacts with participants of GROUP A, B, and C in order to send the invitation to the Follow Up on May 20, 2011

- May 20, 2011: Follow Up with all A, B, and C GROUPS

+ Contact with partners of the project

+ Contact with participants of the various groups

SDE Milestones

19th November 2010: Send out financial guideline for the interim report

20th December 2010 collect material from partners for the interim report. Deadline for report 30. January 2011

15. December 2010: Collect and compile 4th quarterly report.

15th December 2010: Guide for teacher training courses (DK+TR)

January –July 2011. Sparring and feed back in relation to teacher training courses in LT, TR and IT.

6th January 2011: Newsletter

31. March 2011: Collect and compile fifth quarterly report